## Slide 1: Contracting Challenges & Change Control During Uncertainty

## Slide 2: THE SITUATION
A FAR based cost reimbursement contract was competitively awarded for the concurrent design and construction of a “Marble Separation and Bagging Facility”
  A first of a kind marble separation and bagging facility
The contract contains a scope, schedule and estimated price

## Slide 3: THE SCOPE
The Contractor is to design, construct and commission a series of large facilities that separate and bag marbles. These facilities must be compliant with complex laws, rules and regulations dealing with the disposition of various colors, sizes and weights of marbles
All the primary colored marbles (assumed to be majority of the marble inventory) are to be separated from the non-primary colored marbles in the Marble Separation Facility (MSF)
Once separated the two sets of marbles are sent to either the primary color marble bagging facility (PCMBF) or the non-primary color marble bagging facility (NPCMBF)
Once bagged another contractor is responsible for transportation and disposal of the marbles
The primary color marbles are slightly hazardous
The non-primary color marbles can be highly toxic and potentially deadly depending on the specific color and their weight or size.
  Purple marbles are the worst of the worst. If put in a certain configuration can create a deadly purple flash
  However, it was assumed in the beginning that no purple marbles could be sent to the MSF based on calculations and knowledge of the marbles in the tanks
Many other assumptions have to be made because the marbles are mixed in with mud in huge tanks. So the actual number of the different colors, weights and sizes of the marbles is unknown
Also, the marbles can/might change color, size and weight over time, with the expectation that the marbles become less toxic and less hazardous as time passes

## Slide 4: THE SCHEDULE
The schedule for completion was 5 years
As change occurred for a variety of reasons the schedule has been extended
Based on recent events the schedule might have to be adjusted again

## Slide 5: THE ESTIMATED PRICE
The type of contract is a Cost Plus Award Fee
  The Total Estimated Contract Cost (TECC) is established in section B
  The Fee is established in section B
  The total of the TECC and Fee is the Total Estimated Contract Price (TECP)

## Slide 6: FAR Based Contracting
Concepts to Consider
  Vast majority of contracts issued under the FAR are
    Fixed Price
    Buying commodities
    Completed in less than a year
  The FAR is built around buying stuff
    But does contain sections on how to buy construction services
    Does contain a section on how to deal with changes

## Slide 7: FAR Based Contracting
FAR Part 1.102 states
    “The role of...Team is to exercise personal initiative and sound business judgment in providing the best value...to meet the customers needs. In exercising initiative Government members...may assume if a specific strategy, practice, policy or procedure is in the best interests of the Government and is not addressed in the FAR or prohibited by law...that the strategy, practice, policy or procedure is a permissible exercise of authority”
FAR Part 1.602-2 states
    “...contracting officers should be allowed wide latitude to exercise business judgment. Contracting Officers shall-
      (b) Ensure that contractors receive impartial, fair and equitable treatment”

## Slide 8: CONTRACTING WITH UNCERTAINTY AND CHANGE
The typical clauses in a cost reimbursement contract provide both parties significant rights as well as responsibilities in dealing with change
These clauses can be used to protect the parties interests when there is uncertainty and change
However, the exercise of sound business judgment is key to the successful use of these clauses

## Slide 9: How Do you Contract with Uncertainty?
Several Key Decisions must be made
  Do you attempt continued performance?
  Are there adequate protections for the parties?
  Do you have provided/received sufficient direction to understand what is expected/performed?

## Slide 10: Contracting with Uncertainty
The following approach outlined assumes:
  The parties want continued performance
    I.E. the benefits of continued performance outweigh the potential risks
    Informed decision making a must
  There are adequate protections
    Both parties are comfortable with continued performance
    Both parties understand their rights and responsibilities
  There is sufficient direction
    The continued performance expectation is clear
    The continued performance expectation really has to be in writing for this approach to work (i.e. ensure adequate protections)

## Slide 11: THIS IS HOW
USE THE POWER OF FAR BASED COST REIMBURSEMENT CONTRACTING
  FAR 16.301-2 “...are suitable for use only when uncertainties involved in contract performance do not permit cost to be estimated with sufficient accuracy to use any type of fixed-price contract”
    REMEMBER UNCERTAINTY IS A GIVEN FOR COST RE
  Contain Limitation of Costs or Limitation of Funds
    Very powerful protections for both parties
  “Changes Cost Reimbursement”
  Should contain “Notification of Changes”
    Powerful authority is granted to the Contractor

## Slide 12: THE HOW
  FAR 52.232-22 “LIMITATION OF FUNDS”
    The ultimate protection for both parties
      Government’s liability is capped at funds obligated
      Contractor does not have to perform if they think there isn’t enough obligated funds
    Once the Contractor has declared insufficient funds the Government must upon Contractor’s request-
        Obligate more funds
        Descope
        Terminate for Convenience (T for D is extremely difficult)
    By the way Contractors read paragraph (l) of 52.232-22 some time

## Slide 13: THE HOW CONTINUED
Be very judicious regarding the use of the Changes Clause
  Many Agency regulations require NTE’s in Change Orders
    No exception made for Cost Re contracts
    Think that through for a minute
      What does an NTE in a Cost Re contract really accomplish?
Rather recommend issuing formal letters of direction by the CO

## Slide 14: MORE HOW
Notification of Changes FAR 52.243-7
  Best clause ever – Contains one of the longest sentences known to man
  (c) Continued Performance.
  “Following submission of the notice required by paragraph (b) of this clause, the Contractor shall diligently continue performance of this contract to the maximum extent possible in accordance with its terms and conditions as construed by the Contractor, unless the notice reports a direction of the Contracting Officer or a communication from a SAR of the Contracting Officer, in either of which events the Contractor shall continue performance; provided, however, that if the Contractor regards the direction or communication as a change as described in paragraph (b) of this clause, notice shall be given in the manner provided.”
  (a 98 word sentence in case you were counting)

## Slide 15: MORE HOW CONTINUED
How to use the “Notification of Changes”
  Contractor’s responsibility to provide appropriate notice and continue performance the best of their ability
  Government’s responsibility to either
    Confirm change and direct further performance
    Countermand any communication regarded as a change
    Deny change and direct further performance
    Determine notice is inadequate to make a decision and request further information
  Is there harm in using the last bullet?
  What are the new risks introduced by using this approach?

## Slide 16: Other Points to Ponder
Change Orders and Contractor’s Assertion of Rights
  Suppose the Government issued a massive change order for billions of dollars
  Suppose the Contractor chose to not assert their right to a change
  What then?
Equitable Adjustment Requests
  Suppose the Government agreed there is entitlement for change for billions of dollars
  Suppose the Government rejected the equitable adjustment request quantum
  Suppose the Contractor said “so?”
  What then?

## Slide 17: IN SUMMARY
Cost Reimbursement Contracting is by definition full of uncertainty
Demonstrate and exercise sound business judgment
Contracting Professionals can use the power of the FAR to either hinder or enable continued performance
Be careful what you sign, as the contract matters
  Don’t waive away your rights under the Limitation of Funds Clause
  Provide timely notices to protect your entitlement to change

## Slide 18: The End
Questions?
  Answers optional